## Vendor Readiness Timeline
Alabama Medicaid Agency-ACHN Program
Vendor Readiness Schedule (dates subject to change)
2024-04-19 | 2024-04-19 | Intent to Award Notification.
2024-05-06 09:00 | 2024-05-10 09:00 | Mandatory ACHN Vendors On-Site Orientation held at Alabama Medicaid Offices. 3-Day Session. Start Date and time is TBA.
2024-06-06 | 2024-06-27 | Vendors develop Implementation Plan.
2024-05-20 | 2024-06-21 17:00 | Vendors Complete Provider Enrollment w/Gainwell & Data Connections.
2024-06-06 | 2024-07-27 | Complete Data Exchange and Testing with AMA HIE.
2024-06-06 | 2024-06-27 | Vendor Readiness Documents Due to Agency.
2024-06-24 09:00 | 2024-07-23 17:00 | Develop & Submit Technical Implementation Plan for HMS per GRC Requirements
2024-06-06 | 2024-07-22 | Vendors update AMA GRC tool for ISO - Due 7/22.
2024-06-06 | 2024-09-18 | RFP Readiness Period
2024-06-06 | 2024-08-06 | Initial Agency Site Visit Period for Readiness Assesments. Two Visits per Vendor/Region.
2024-07-22 | 2024-07-22 | GRC Responses are due to AMA.
2024-08-07 | 2024-08-23 17:00 | Final Agency Site Visit period for each Vendor/Region.
2024-08-26 09:00 | 2024-08-30 17:00 | Assessment Acceptance Letters Reviewed and Mailed to ACHN Vendors.
2024-09-05 09:00 | 2024-09-05 09:00 | Contract Review Committee.
2024-09-18 09:00 | 2024-09-18 09:00 | All Readiness Requirements Must Be Complete.
2024-10-01 | 2024-10-01 | Official Contract Award. ACHN services begin.